## InputData
Wye Creek Project
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Task | 2001-06-25 | 2001-07-03 | 2001-07-11 | 2001-07-19 | 2001-07-27 | 2001-08-04 | 2001-08-12 | 2001-08-20 | 2001-08-28 | 2001-09-05 | 2001-09-13 | 2001-09-21 | 2001-09-29 | 2001-10-07 | 2001-10-15 | 2001-10-23 | 2001-10-31 | 2001-11-08 | 2001-11-16 | 2001-11-24 | 2001-12-02 | 2001-12-10
Project Brief
Concept Plans
Electrical SLD
General Arrangement
Linework Overview
Linework
Extend 11kV line
Change transformers
Set up supply agreements
Commission
Substation
Detailed electrical design
Fault calculations & protection design
Control & protection schematics
Specify & order CB
CB delivery
Earthing design
Panel layouts & positioning
Detailed civil design
Earthing layout & ducting
Foundations & formwork
Bunding
Fencing
Construction - civil
Site preparation
Excavation
Earthing & other embedded items
Foundations & formwork
Bunding
Fencing
Construction - electrical
Prewire panels
Substation modifications
Install CB
Install panels
Cabling & terminations
Metering
Pre-commissioning testing
Commission
Project close-out

## BudgetGannt
Wye Creek Project
Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Task | Cost | Resource | 2001-06-25 | 2001-07-03 | 2001-07-11 | 2001-07-19 | 2001-07-27 | 2001-08-04 | 2001-08-12 | 2001-08-20 | 2001-08-28 | 2001-09-05 | 2001-09-13 | 2001-09-21 | 2001-09-29 | 2001-10-07 | 2001-10-15 | 2001-10-23 | 2001-10-31 | 2001-11-08 | 2001-11-16 | 2001-11-24 | 2001-12-02 | 2001-12-10 | 2001-12-11 | 2001-12-12
Project Management | 12000 | SEL | [8 empty] | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750
Project Brief |  | SEL | bar: 1
Concept Plans
Electrical SLD | 500 | SEL | 2: 500
General Arrangement | 1500 | SEL | 2: 1500
Linework Overview | 500 | SEL | 3: 500
Linework | 24000 | DELTA??
Set up supply agreements |  |  | 12: 2400
Extend 11kV line |  |  | 14: 9600
Change transformers |  |  | 15: 9600
Commission |  |  | 16: 2400
Substation
Detailed electrical design
Fault calculations & protection design | 3000 | SEL | 3: 3000
Control & protection schematics | 2000 | SEL | 4: 1000; 5: 1000
Specify & order CB | 1500 | SEL | 4: 1500
CB delivery | 60000 | MHL | 20: 60000
Earthing design | 1500 | SEL | 5: 1500
Panel layouts & positioning | 2000 | SEL | 6: 2000
Relay programming | 4000 | SEL | 7: 2000; 8: 2000
Drawings | 3000 | SEL | 3: 750; 4: 750; 5: 750; 6: 750
Detailed civil design
Physical layouts | 1000 | SEL | 5: 500; 6: 500
Earthing layout & ducting | 1000 | SEL | 6: 1000
Foundations & formwork | 1000 | Pioneer | 7: 1000
Bunding | 2000 | SEL | 8: 2000
Fencing | 1000 | SEL | 7: 1000
Drawings | 1500 | SEL | 7: 750; 8: 750
Construction - civil
Site preparation | 500 | Pioneer | 8: 500
Excavation | 1000 | Pioneer | 8: 1000
Earthing & other embedded items | 5000 | Pioneer | 8: 5000
Foundations, formwork & finished surface | 8000 | Pioneer | 9: 4000; 10: 4000
Bunding | 15000 | Pioneer | 9: 7500; 10: 7500
Fencing | 4000 | Pioneer | 11: 4000
Construction - electrical
Prewire panels | 12000 | Pioneer | 7: 6000; 8: 6000
Relay delivery | 10000 | Uniserve | 11: 10000
Substation modifications | 15000 | DELTA?? | 19: 7500; 20: 7500
Install CB | 2000 | Pioneer | 21: 2000
Install panels | 4000 | Pioneer | 9: 4000
Cabling & terminations | 9000 | Pioneer | 10: 9000
Metering | 40000 | DELTA??
Pre-commissioning testing | 500 | Pioneer | 22: 40000
Commissioning |  |  | 22: 500
Preparing commissioning plans | 3000 | SEL | 12: 3000
On-site commissioning | 2000 | SEL | 22: 2000
Comms to Weir
Remove existing equipment | 500 | Pioneer | 6: 500
Install new equipment | 7000 | Pioneer | 7: 7000
House Supply
Install ducting | 1000 | SEL | 8: 1000
Install mains & liven | 1200 | SEL | 8: 1200
Transport | 10000
Project close-out
As-building | 1500 | SEL | 23: 1500
Final documentation |  | SEL | 24: 0
Totals | 275200 |  | 0 | 2000 | 4250 | 3250 | 3750 | 4750 | 17750 | 19450 | 16250 | 21250 | 14750 | 6150 | 750 | 10350 | 10350 | 3150 | 750 | 750 | 8250 | 68250 | 2750 | 43250 | 2250 | 750 | 265200
| Month | Per Month | 1: Budget
| July | 13250 | 1: 13250
| August | 58200 | 1: 71450
| September | 42900 | 1: 114350
| October | 24600 | 1: 138950
| November | 77250 | 1: 216200
| December | 49000 | 1: 265200
265200

## Scorpion
Wye Creek Project
Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Task | Cost | Resource | 2001-06-25 | 2001-07-03 | 2001-07-11 | 2001-07-19 | 2001-07-27 | 2001-08-04 | 2001-08-12 | 2001-08-20 | 2001-08-28 | 2001-09-05 | 2001-09-13 | 2001-09-21 | 2001-09-29 | 2001-10-07 | 2001-10-15 | 2001-10-23 | 2001-10-31 | 2001-11-08 | 2001-11-16 | 2001-11-24 | 2001-12-02 | 2001-12-10 | 2001-12-18 | 2001-12-26
Project Management | 12000 | SEL | [8 empty] | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750
Project Brief |  | SEL | bar: 1
Concept Plans
Electrical SLD | 500 | SEL | 2: 500
General Arrangement | 1500 | SEL | 2: 1500
Linework Overview | 500 | SEL | 3: 500
Linework | 0 | DELTA??
Set up supply agreements |  |  | 12: 0
Extend 11kV line |  |  | 14: 0
Change transformers |  |  | 15: 0
Commission |  |  | 16: 0
Substation
Detailed electrical design
Fault calculations & protection design | 3000 | SEL | 3: 3000
Control & protection schematics | 2000 | SEL | 4: 1000; 5: 1000
Specify & order CB | 1500 | SEL | 4: 1500
CB delivery | 0 | MHL | 20: 0
Earthing design | 1500 | SEL | 5: 1500
Panel layouts & positioning | 2000 | SEL | 6: 2000
Relay programming | 4000 | SEL | 11: 2000; 12: 2000
Drawings | 3000 | SEL | 3: 750; 4: 750; 5: 750; 6: 750
Detailed civil design
Physical layouts | 1000 | SEL | 5: 500; 6: 500
Earthing layout & ducting | 1000 | SEL | 6: 1000
Foundations & formwork | 0 | Pioneer | 7: 0
Bunding | 2000 | SEL | 8: 2000
Fencing | 1000 | SEL | 7: 1000
Drawings | 1500 | SEL | 7: 750; 8: 750
Construction - civil
Site preparation | 0 | Pioneer | 8: 0
Excavation | 0 | Pioneer | 8: 0
Earthing & other embedded items | 0 | Pioneer | 8: 0
Foundations, formwork & finished surface | 0 | Pioneer | 9: 0; 10: 0
Bunding | 0 | Pioneer | 9: 0; 10: 0
Fencing | 0 | Pioneer | 11: 0
Construction - electrical
Prewire panels | 0 | Pioneer | 7: 0; 8: 0
Relay delivery | 0 | Uniserve | 11: 0
Substation modifications | 0 | DELTA?? | 19: 0; 20: 0
Install CB | 0 | Pioneer | 21: 0
Install panels | 0 | Pioneer | 9: 0
Cabling & terminations | 0 | Pioneer | 10: 0
Metering | 0 | DELTA??
Pre-commissioning testing | 0 | Pioneer | 22: 0
Commissioning |  |  | 22: 0
Preparing commissioning plans | 3000 | SEL | 12: 3000
On-site commissioning | 1000 | SEL | 22: 1000
Comms to Weir
Remove existing equipment | 0 | Pioneer | 6: 0
Install new equipment | 0 | Pioneer | 7: 0
House Supply
Install ducting | 1000 | SEL | 8: 1000
Install mains & liven | 1200 | SEL | 8: 1200
Transport | 0
Project close-out
As-building | 1500 | SEL | 23: 1500
Final documentation |  | SEL | 24: 0
Totals | 45700 |  | 0 | 2000 | 4250 | 3250 | 3750 | 4250 | 1750 | 4950 | 750 | 750 | 2750 | 5750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 1750 | 2250 | 750 | 45700
| Month | Per Month | 1: Budget
| July | 13250 | 1: 13250
| August | 11700 | 1: 24950
| September | 10000 | 1: 34950
| October | 3000 | 1: 37950
| November | 2250 | 1: 40200
| December | 5500 | 1: 45700
45700